## Remobilisation
Association for Cultural Enterprises - Draft Mobilisation Plan for Catering Post Covid-19
Location: | Task Lead | Commencement Date | 2020
|  |  | Pre-Opening Mobilisation Phase |  |  |  | Launch Phase |  | Operational Phase
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Ongoing
Action
Mobilisation & Online Meeting Schedule
Distribute Mobilisation Plan
Kick off meeting
Meeting - facilities and equipment; space planning; new equipment e.g. screens
Meeting - staff and training
Meeting - operational planning and health and safety; distancing measures
Meeting - food and beverage
Meeting ‐ logistics
Contractual & Legal
Variations to contract terms
Agree variations
Contract variations to legal teams
Facilities
Deep cleaning of all areas
Kitchen Equipment maintenance
Front of House Equipment maintenance
Furniture cleaning
All equipment - full testing carried out (pressure vessel etc.)
Additional equipment - instalment of screens, distancing tools, sanitising stations
HR - Structure
Agree variations in team structure
Agree shift patterns to support social distancing
Prepare costed rota templates
HR - L&D - Induction & Training
Training planning meeting
Amendments to training programme
Retraining - Food Safety and H & S with Covid-19 updates
Ensure all team members are fully trained on all risk assessments
Chemical control and cleaning update
Food/kitchen training; new menus and practices
Operational On-The-Job Training
HR - Welfare
Design and install internal notice boards
Mental health awareness and support
HR - Communication and Briefings
Arrange advance and pre-opening brieﬁngs
Arrange and coordinate feedback from the operational teams during training and initial mobilisation period
Quality Management Systems
Agree reporting mechanisms against revised KPIs
Agree amendments to Service Level Agreements
Update Operations Manual
Customer journey updated
Update Business Continuity Plan
Marketing
Agree pre-launch marketing and press
Confirm policy on event business
F&B - Menus
Review menu concept, service delivery style and process, for all areas
Ensure all allergens are identified and highlighted throughout food journey
Update allergen control policy
Finalise all recipes
Review menu costings and selling prices for possible supply price changes
SOPs for food production
SOPs for food service
F&B - Procurement
Engage with existing and new suppliers
All stock items entered into procurement system
Stock and order sheets set up
Opening notifications issued to all current suppliers including delivery rules
Disposable Packaging
Explore packaging options in line with the service and menu requirement
Source packaging and disposables
F&B - Pre-Opening Orders
Conﬁrm product requirements
Place food orders
Place beverage orders
Place disposable orders
Conﬁrm delivery dates
Arrange logistics team for delivery days
H&S - Legislation
Arrange installation of updated H&S signage
Ensure Pest Control requirements are met
Update Risk Assessments and SSW
H&S - COSHH
Contact chemical/PPE supplier to conﬁrm requirements
Conﬁrm chemicals requirement
Chemical Dosing system install as relevant
Identify the level of PPE required for each job
Order PPE to meet all requirements
Ensure secure chemical storage unit is in position
IT
EPOS update
IT requirements for cashless payments
IT equipment tested
Finance - P&L/Forecasting/Budgets
Update capex register
Update P&L
Update financial forecast
Finance - Controls
Prepare & provide par stock sheets, control sheets & wastage docs
Ensure opening stock is accounted for
Finance - Client Reporting
Agree timelines and format for financial reporting